## Foglio1
Product backlog item | Tasks | Acceptance criteria | Story points
As a player I want to move both right and left so that I can avoid obstacles. | 1. Create a character; 2. Implement right and left movement with keyboard input; 3. Anchor character to a fixed trajectory; 4. Impement left and right boundaries. | Verify that the character can go only to the left and to the right within the defined boundaries. | 8
As a player I want obstacles so that they act as hindrance. | 1. Create obstacle object; 2.Insertion of the elements in the scene. | Verify the correct presence of the object in the scene | 21
As a player I want the obstacles to fall down so that the game is more challenging. | 1.Implement the random fall of obstacles; 2.Implement disappearance of obstacles when they touch the character or the ground. | Verify that the obstacle disappears when touches the character or the ground. | 13
As a player I want health bar so that I am aware of the remaining points before dying. | 1. Implement the health bar; 2. Update by decreasing health when the character is touched by an obstacle; 3. When the health bar reaches 0, the game stops. | Verify that the bar adjusts according to health points and that the game stops when the health points are 0. | 3
As a player,once I reach a certain score I have to fight against a boss with his own heathbar in order to go forward. | 1.Create the boss; 2.Make sure that a different boss appears at the appropriate time cyclically,after a fixed amount of time; 3.Create the healthbar of the boss. | Verify that the boss appears correctly at the right moment and accordingly its healthbar is displayed. | 21
As a player I want that the boss character can shoot me to make the game more difficult. | 1.Draw a bullet that falls from the boss' position; 2.Ensure that the character's life and score are decremented if it is hit; 3.Make sure that when the boss is hit you increase the character's score and the boss's life is decreased. | Make sure that the boss shoots downwards and when it occurs, the right animation is displayed. | 13
As a player I want to reach bonus in order to recharge my life or to be safe of obstacles. | 1.Creating falling down bonus; 2.Implement the effect of the falling down bonus. | Ensure that the bonus fall down and the characters react correctly when they are hit by bonus. | 8
As a player I want to hear sound effects in order to make the game more exciting. | 1.Set the sound when professors are hit by Pepper's bullets; 2.Set the sound when professors hit Pepper; 3.Set the sound when boss its Pepper; 4.Set the sound when boss is hit by Pepper's bullets. | Ensure that it is possible to hear the sounds. | 8
As a player I want that the boss can follow the movements of my character to make the game more exciting. | 1.Make sure the boss is properly positioned in the scene in order to follow Pepper; 2.Move the boss horizontally according to the character's position. | Ensure that the boss follows Pepper properly. | 5
As a player I want to make the difficulty of the boss increasing during the game in order to make the game more exciting. | 1.Set the increasing speed of the boss and of its bullets. | Ensure that the difficulty of the boss increases. | 3
As a player I want the obstacles to disappear when the boss character enters the scene. | 1.Make the obstacles disappear when the boss appears in the scene. | Make sure that the obstacles aren't displayed when the boss appears. | 3
As a player I want to keep track of my score while I’m playing so that I can improve it. | 1.Create a specific lable in the HUD of the game. | Ensure that the score is updated correctly. | 2
As a player I want a menu in order to set the difficulty of the game, start a new game, or exit by. | 1.Create the menu; 2.Create the background of the menu. | Ensure that the menu works properly. | 2
As a player I want a sound track for the game. | 1.Add a sound track when main menu is displayed. | Ensure that is possible to hear the soundtrack when I visualize the main menu. | 2
As a player I want to add a background for my game in order to make it more pretty. | 1.Set the background. | Ensure that it is possible to see the correct background. | 1
As a player I want to see my professors as obstacles. | 1.Set image of obstacles as professors; 2.Set the random generation of the professors. | Ensure that the obstacles have the faces of professors. | 1