## Foglio1
Product backlog item | Sprint task | Acceptance criteria | Story points
As a player,once I reach a certain score I have to fight against a boss with his own heathbar in order to go forward. | 1.Create the boss; 2.Make sure that a different boss appears at the appropriate time cyclically,after a fixed amount of time; 3.Create the healthbar of the boss. | Verify that the boss appears correctly at the right moment and accordingly its healthbar is displayed. | 21
As a player I want that the boss character can shoot me to make the game more difficult. | 1.Draw a bullet that falls from the boss' position; 2.Ensure that the character's life and score are decremented if it is hit; 3.Make sure that when the boss is hit you increase the character's score and the boss's life is decreased. | Make sure that the boss shoots downwards and when it occurs, the right animation is displayed. | 13
As a player I want to reach bonus in order to recharge my life or to be safe of obstacles. | 1.Creating falling down bonus; 2.Implement the effect of the falling down bonus. | Ensure that the bonus fall down and the characters react correctly when they are hit by bonus. | 8
As a player I want to hear sound effects in order to make the game more exciting. | 1.Set the sound when professors are hit by Pepper's bullets; 2.Set the sound when professors hit Pepper; 3.Set the sound when boss its Pepper; 4.Set the sound when boss is hit by Pepper's bullets. | Ensure that it is possible to hear the sounds. | 8
As a player I want that the boss can follow the movements of my character to make the game more exciting. | 1.Make sure the boss is properly positioned in the scene in order to follow Pepper; 2.Move the boss horizontally according to the character's position. | Ensure that the boss follows Pepper properly. | 5
As a player I want to make the difficulty of the boss increasing during the game in order to make the game more exciting. | 1.Set the increasing speed of the boss and of its bullets. | Ensure that the difficulty of the boss increases. | 3
As a player I want the obstacles to disappear when the boss character enters the scene. | 1.Make the obstacles disappear when the boss appears in the scene. | Make sure that the obstacles aren't displayed when the boss appears. | 3
As a player I want to keep track of my score while I’m playing so that I can improve it. | 1.Create a specific lable in the HUD of the game. | Ensure that the score is updated correctly. | 2
As a player I want a menu in order to set the difficulty of the game, start a new game, or exit by. | 1.Create the menu; 2.Create the background of the menu. | Ensure that the menu works properly. | 2
As a player I want a sound track for the game. | 1.Add a sound track when main menu is displayed. | Ensure that is possible to hear the soundtrack when I visualize the main menu. | 2
As a player I want to add a background for my game in order to make it more pretty. | 1.Set the background. | Ensure that it is possible to see the correct background. | 1
As a player I want to see my professors as obstacles. | 1.Set image of obstacles as professors; 2.Set the random generation of the professors. | Ensure that the obstacles have the faces of professors. | 1
Done criteria: For our team a task is completed when it has passed the single unit tests and the integration tests.
Goal: Develop a version of the game in which the character can fight against a boss ciclically, after a fixed amount of time, and the boss's health bar displays the correct amount of its health points. The boss can shoot the caracter and follow him. Once the boss's health bar is empty, the boss disappears and the game go ahead.
Estimated velocity : 69