## Foglio1
Product backlog item | Sprint task | Acceptance criteria | Story points
As a player I want to move both right and left so that I can avoid obstacles. | 1. Create a character; 2. Implement right and left movement with keyboard input; 3. Anchor character to a fixed trajectory; 4. Impement left and right boundaries. | Verify that the character can go only to the left and to the right within the defined boundaries. | 8
As a player I want obstacles so that they act as hindrance. | 1. Create obstacle object; 2.Insertion of the elements in the scene. | Verify the correct presence of the object in the scene | 21
As a player I want the obstacles to fall down so that the game is more challenging. | 1.Implement the random fall of obstacles; 2.Implement disappearance of obstacles when they touch the character or the ground. | Verify that the obstacle disappears when touches the character or the ground. | 13
As a player I want health bar so that I am aware of the remaining points before dying. | 1. Implement the health bar; 2. Update by decreasing health when the character is touched by an obstacle; 3. When the health bar reaches 0, the game stops. | Verify that the bar adjusts according to health points and that the game stops when the health points are 0. | 3
In order to destroy an obstacle , as a player, I want to be able to shoot so that I can increase my score. | 1.Create the missile object; 2.Implement missile upward movement; 3.Take care of the collision between missile and obstacle; 4.Create Pepper's animation during the shot. | Check that the character shoots correctly and that a correct collision occurs between the missile and the obstacle. | 21
Done criteria: For our team a task is completed when it has passed the single unit tests and the integration tests.
Goal: Our goal is to make a working first demo of game, with pepper able to move on a certain position only left and right, able to dodge books that fall down randomly. The game is equipped with a hud bar that updates whenever pepper hits a book.
Estimated velocity : 66